## Project Pipeline
| PathStone Group | 2022 | IMPROVEMENT PROJECTS DASHBOARD
0 | [7 empty] | 0 | 0
PLANNED 0 | REQUESTED BY | IN PROGRESS 0 | Brief Description | STARTED | PROJECTED HARD SAVINGS | PROJECTED SOFT SAVINGS | PROJECT HEALTH | PROGRESS | COMPLETED 0 | COMPLETED | SAVINGS by the YEAR END | SOFT SAVINGS
|  | 0 | [6 empty] | 0
|  | OTHER ACTIVITIES 0 | REQUESTED BY | STARTED | ESTIMATED COMPLETION | STATUS | PROJECT HEALTH | PROGRESS | PAUSED / CANCELED 0 | STATUS | REASON | ESTIMATED SAVINGS
|  | TOTAL PROJECTED PIPELINE SAVINGS |  |  | 0 |  |  |  | TOTAL YTD SAVINGS | 0

## Priority Matrix
IMPACT-EFFORT PRIORITY MATRIX
HIGH | 🕺 |  |  |  | 💰
|  | QUICK WINS |  | TOP PRIORITY - STRATEGIC
IMPACT
|  | INCREMENTAL IMPROVEMET |  | TIME WASTE
| 👍 |  |  |  | 💀
LOW
EFFORT
LOW

## Project Pipeline (EXAMPLE)
| PathStone Group | 2022 | IMPROVEMENT PROJECTS DASHBOARD
1 | [7 empty] | 8 | 9
PLANNED 1 | REQUESTED BY | IN PROGRESS 8 | Brief Description | STARTED | PROJECTED HARD SAVINGS | PROJECTED SOFT SAVINGS | PROJECT HEALTH | PROGRESS | COMPLETED 9 | COMPLETED | SAVINGS by the YEAR END | SOFT SAVINGS
Primary KPI and CI opportunities | Amador | ES Consolidation - SOP4110 |  | 2022-01-15 | 60000 | 876 hours saved | Good | 80% | Packaging Supplies Kitting (PackRooms Kanban) | 2022-02-04 | 45000 | Communication improved, less stress, even workload
|  | Station 6 (SMED) |  | 2022-06-15 | 230000 | Availability, C/O Time | Excellent | 95% | Materials Kanban (Supply Room) Phase 1 | 2022-02-11 | 247000 | Communication improved, less stress, even workload
|  | Procurement Improvement |  | 2022-07-26 | 123000 | Communication | Good | 60% | Lean Training GEN 1 Projects | 2022-05-24 | 320000 | Skills / Lean Transf
|  | Line 3 Labor Optimization |  | 2022-08-15 | 34000 | WIP reduction | Excellent | 10% | Line 5 Optimization (Labour cost) | 2022-05-24 | 123000 | WIP Reduction
|  | Line 4 Labor Optimization |  | 2022-08-15 | 231000 | WIP reduction | Excellent | 10% | Line 5 Optimization (SMED Changeover) | 2022-07-22 | 30000 | Availability
|  | Packer Labor Optimization |  | 2022-08-15 | 4500 | WIP reduction | Excellent | 20% | Waste Reduction (Granolas line) | 2022-06-15 | 70000 | * Verify, Mat. Eff; Waste
|  | Batch Release Improvement |  | 2022-08-01 | 32400 |  | Mediocre | 10% | RTV Process Design | 2022-07-22 | 70000 | Communication, balanced team activities
|  | On Hold Process |  | 2022-08-22 | 6500 |  | Excellent | 5% | Lean Training GEN 2 Projects | 2022-08-12 | 457000 | Skills / Lean Transf
[9 empty] | Barcode Error Proofing Tool | 2022-08-12 | 100000 | Error proofing
|  | 13 | [6 empty] | 6
|  | OTHER ACTIVITIES 13 | REQUESTED BY | STARTED | ESTIMATED COMPLETION | STATUS | PROJECT HEALTH | PROGRESS | PAUSED / CANCELED 6 | STATUS | REASON | ESTIMATED SAVINGS
|  | Reviving CI Newsletter | Sam | 2022-05-01 | - | Completed | Excellent | 100% | Extraction Storage Capacity | Canceled | Handed over to Eng. | unknown
|  | Lean Training Program | Sam | 2022-02-21 | - | Completed | Excellent | 100% | Milling optmization (P) | Paused | Low priority | 100000
|  | SWI Update for all Process Rooms | Sam | 2022-06-15 | 2022-06-30 | Completed | Good | 100% | Line 5 - Failure controls (Part of FMEA Pack 5) (P) | Paused | Low priority | N/A
|  | OEE Daily Tracking (Shift Reports, Dashboards, BSC) | William | 2022-05-15 | 2022-07-15 | Completed | Good | 100% | Line 3 - Failure Controls (Part of FMEA Pack 3) (P) | Paused | Low priority | N/A
|  | 5S Training (SCM team ) | Gray | 2022-03-01 | 2022-03-02 | Completed | Excellent | 100% | Scheduling Auto-Planner | Canceled | No Buy-In | N/A
|  | Kanban Training (SCM team ) | Gray | 2022-03-03 | 2022-03-03 | Completed | Excellent | 100% | VSM - Supply Chain (LT reduciton opportunities) | Paused | Low priority | N/A
|  | CI Board | Edgar | 2022-03-01 | 2022-06-01 | Completed | Good | 100%
|  | 5Whys + Root Cause Training (CAPA solving) | Tim | 2022-06-23 | 2022-06-23 | Completed | Excellent | 100%
|  | KPI Summary Report Automation | Edgar | 2022-08-01 | 2022-08-05 | Completed | Excellent | 100%
|  | Sanitation - Revised Request Form | Norma | 2022-08-01 | 2022-08-15 |  | Excellent | 10%
|  | Primary - Revised Shift Report | Amir | 2022-06-15 | 2022-08-01 |  | Excellent | 60%
|  | Finished Goods pallet tags Kanban | Peter | 2022-02-23 | 2022-03-15 |  | Excellent | 50%
|  | Cold wrap Produciton Standard Work | Sam | 2022-02-15 | 2022-02-23 |  | Excellent | 80%
|  | TOTAL PROJECTED PIPELINE SAVINGS |  |  | 721400 |  |  |  | TOTAL YTD SAVINGS | 1462000